## Sheet1
KitchenPluss AI Integration Plan |  |  |  | PROJECT SPRINT
4-Week Technical Roadmap • FastAPI Microservice, RAG Pipeline, LangGraph & Mobile Integration |  |  |  | 20 Working Days Total
TOTAL TASKS |  | COMPLETED | IN PROGRESS | BLOCKED | COMPLETION RATE
20 Work Days Planned |  | Done & Verified | Currently Active | Needs Attention
Week | Day | Learning Focus | Project Task (KitchenPluss implementation) | Manager Update (Stand-up Script) | Status
Week 1: Python Microservice & Kitchen Data Ingestion | Day 1 | Scaffold Python/FastAPI service | Scaffold services/ai-agent/ directory with Python, FastAPI, and Uvicorn. Connect it to the existing docker-compose.yml. | I containerized and scaffolded a dedicated Python/FastAPI AI microservice within our Docker compose stack to isolate LLM agent orchestration from the core API. | Completed
Week 1: Python Microservice & Kitchen Data Ingestion | Day 2 | Next.js Full-Stack & DRY Shared Core | Initialize Next.js 15 App Router in web/ and extract @kitchenpulse/shared monorepo package (Zod schemas, DTOs, types) to eliminate code duplication across web and mobile. | I migrated web to Next.js 15 App Router with full-stack Route Handlers and extracted @kitchenpulse/shared to eliminate duplicate types across web and mobile. | Completed
Week 1: Python Microservice & Kitchen Data Ingestion | Day 3 | Gemini SDK Integration | Integrate Gemini 1.5 Pro / Flash via the Google GenAI SDK with structured outputs. | I established direct Gemini SDK integration in the AI microservice with structured JSON output enforcement. | Completed
Week 1: Python Microservice & Kitchen Data Ingestion | Day 4 | Database Connection (SQLAlchemy) | Connect the Python service to your PostgreSQL database using SQLAlchemy/asyncpg to query real inventory tables. | I enabled read access from the AI microservice to our production PostgreSQL database to allow live state inspection. | Not Started
Week 1: Python Microservice & Kitchen Data Ingestion | Day 5 | SSE Streaming | Expose a streaming SSE endpoint (/api/agent/stream) that the React Native app can listen to for real-time recommendations. | I created a Server-Sent Events (SSE) streaming endpoint in the AI service to deliver real-time token streaming to the mobile client. | Not Started
Week 2: Recipe & SOP Vector Database (RAG over Recipes) | Day 6 | pgvector Setup | Enable the pgvector extension in your existing PostgreSQL database (01_init.sql). | I enabled the pgvector extension on our PostgreSQL instance to support in-database vector embeddings without needing third-party vector DBs. | Not Started
Week 2: Recipe & SOP Vector Database (RAG over Recipes) | Day 7 | Document Embedding Pipeline | Build an embedding pipeline to index recipe instructions, allergen warnings, and prep procedures. | I built an automated embedding script that converts recipe steps and allergen tables into vector embeddings. | Not Started
Week 2: Recipe & SOP Vector Database (RAG over Recipes) | Day 8 | Vector Similarity Search | Implement vector similarity search (cosine distance) to answer queries like "How do I prep garlic confit safely?". | I implemented semantic similarity search directly in Postgres to match kitchen queries against stored prep protocols. | Not Started
Week 2: Recipe & SOP Vector Database (RAG over Recipes) | Day 9 | RAG Pipeline | Assemble the complete RAG pipeline with relevance re-ranking and source attribution. | I completed the RAG retrieval pipeline, grounding AI responses strictly in our validated kitchen standard operating procedures. | Not Started
Week 2: Recipe & SOP Vector Database (RAG over Recipes) | Day 10 | API & Mobile Exposure | Wire the RAG endpoint into the mobile PrepSheetScreen.tsx so chefs can ask real-time questions about recipes. | I exposed the RAG engine via REST and tested context retrieval for kitchen prep procedures. | Not Started
Week 3: Multi-Agent Workflows with LangGraph | Day 11 | LangGraph Basics & State | Install LangGraph and design the Kitchen State Graph: ChefQueryState containing conversation context, kitchen ID, and tool calls. | I began designing our agentic state machine using LangGraph to handle multi-step kitchen logic. | Not Started
Week 3: Multi-Agent Workflows with LangGraph | Day 12 | Inventory Agent Node | Implement node that uses existing supplier-mcp logic to check ingredient levels and flag impending stockouts. | I implemented the Inventory Agent node, enabling autonomous checks against low-stock thresholds. | Not Started
Week 3: Multi-Agent Workflows with LangGraph | Day 13 | Supplier Order Agent Node | Automatically drafts a purchase order if an ingredient drops below the safety margin, utilizing tool calls. | I added an automated supplier ordering tool that drafts purchase orders when stock reaches critical thresholds. | Not Started
Week 3: Multi-Agent Workflows with LangGraph | Day 14 | Supervisor/Router Node | An orchestrator LLM that inspects kitchen events and routes to either Prep Optimization or Supplier Restock. | I built a supervisor agent graph that routes events between inventory management, prep optimization, and order fulfillment. | Not Started
Week 3: Multi-Agent Workflows with LangGraph | Day 15 | State Persistence | Implement state persistence using Postgres checkpointer (langgraph-checkpoint-postgres). | I added PostgreSQL checkpointers to our agent workflows, ensuring conversations and active runs survive service restarts. | Not Started
Week 4: Mobile & Web Integration (Connecting the React Native Stack) | Day 16 | KDS WebSocket Optimization & Mobile Sync | Optimize Socket.IO channels for sub-50ms latency across kitchen stations and configure offline reconnect buffers for tablets. | I optimized the real-time KDS Socket.IO channels for sub-50ms latency and configured offline event queuing for kitchen tablets. | Not Started
Week 4: Mobile & Web Integration (Connecting the React Native Stack) | Day 17 | Unified API Routes & Socket Server | Migrate Express API routes to Next.js Route Handlers (app/api/*) and attach custom Socket.IO server.ts for live KDS real-time events. | I migrated backend routes into Next.js Route Handlers, serving both Web Server Components and the mobile Expo tablet app from a single API with live Socket.IO. | Not Started
Week 4: Mobile & Web Integration (Connecting the React Native Stack) | Day 18 | React Native Bottom Sheets & DRY UI | Build animated AI Recommendations sheet in mobile using React Native Reanimated and shared Zod schemas to review and approve draft supplier orders. | I created a bottom sheet interface in React Native utilizing shared Zod schemas to review and approve AI-generated supplier orders. | Not Started
Week 4: Mobile & Web Integration (Connecting the React Native Stack) | Day 19 | E2E Integration & Bundle Optimization | Verify end-to-end flow: Mobile ticket firing -> Next.js API & Socket.IO -> AI Agent audit -> Bundle size optimization check. | I ran end-to-end tests validating the unified Next.js + Mobile flow and confirmed significant client bundle size reductions via React Server Components. | Not Started
Week 4: Mobile & Web Integration (Connecting the React Native Stack) | Day 20 | Dockerization & Unified Deployment | Containerize unified Next.js full-stack + Python AI Agent + Postgres/pgvector stack with Docker Compose for production deployment. | I containerized the full unified Next.js + Python AI microservice stack in Docker Compose, achieving a single consolidated deployment. | Not Started

## Next.js Architecture Plan
KitchenPulse — Next.js Full-Stack & DRY Monorepo Architecture Plan
Autonomous Commercial Kitchen Operations: Unified Next.js API, Shared Zod Core, and Client Bundle Reduction
1. ARCHITECTURAL COMPARISON: VITE + EXPRESS vs. NEXT.JS FULL-STACK
Architectural Dimension | Current (Vite SPA + Express API) | Target (Next.js 15 Full-Stack + Shared Core) | DRY & Performance Impact | Mobile Benefit
Code Duplication (DRY) | Types and Zod schemas manually synced across 3 folders (backend, web, mobile) | Single Source of Truth in @kitchenpulse/shared (Zod schemas, types, DTOs) | 100% elimination of redundant validation and DTO code | Directly imports shared models into Expo app
API Architecture | Separate Express server (port 5000) + Vite proxy (port 3000) | Unified Next.js App Router Route Handlers (app/api/* on port 3000) | Consolidates deployment to 1 Node server instead of 2 | Expo mobile hits same /api endpoints as Web
Web Bundle Size | Vite bundles entire SPA (~358 KB client JS initial load) | React Server Components (RSC) render heavy UI on server; client JS reduced by ~45-60% | Zero client JS for static views; fast initial load on slow kitchen tablets | Web preview runs faster with less memory
Mobile App Size | Duplicate client models, manual fetch wrappers | Tree-shaken shared SDK; imports only active query hooks | Reduces overall APK/IPA bundle footprint | Synchronous MMKV + shared queries = instant startup
Real-Time KDS (Socket.IO) | Native Socket.IO on Express server (port 5000) | Custom Next.js Node server (server.ts) binding Socket.IO to http.Server | Retains sub-100ms real-time kanban transitions on port 3000 | Mobile and Web listen to same ws:// room channels
Python AI Microservice | FastAPI microservice on port 8000 in Docker | FastAPI microservice on port 8000 preserved for Gemini/LangGraph | Separation of Concerns: Python excels at AI; Node/Next.js at UI/API | Direct SSE and REST streaming to both clients
2. 5-PHASE EXECUTION ROADMAP & DRY IMPLEMENTATION
Phase | Milestone / Deliverable | Core Technical Tasks | Expected Outcome | Target Week
Phase 1: Core Extraction | packages/shared Package | Create @kitchenpulse/shared npm workspace. Extract Zod schemas (CreateTicket, Ingredient), TypeScript types, and food cost formulas. | Single source of truth for Web, Mobile, and Backend | Week 4 (Day 16)
Phase 2: Next.js Scaffold | Next.js 15 + Custom Server | Initialize Next.js 15 App Router in web/. Implement server.ts wrapping http.createServer with Socket.IO support. | Consolidated server runtime supporting both SSR and WebSockets | Week 4 (Day 16)
Phase 3: Route Handlers | Unified REST API (app/api/*) | Migrate Express routes (/api/auth, /tickets, /ingredients, /supplier-orders) to Next.js Route Handlers. | All HTTP APIs unified; Express server deprecated | Week 4 (Day 17)
Phase 4: Mobile Integration | Expo Client Re-alignment | Point mobile API client to Next.js API. Import shared types and Zod models from @kitchenpulse/shared. | Mobile and Web share exact same validation and client types | Week 4 (Day 18-19)
Phase 5: Optimization & Ship | Bundle Analysis & Docker | Run Next.js Bundle Analyzer. Verify RSC reduction. Update docker-compose.yml to run unified web + ai-agent + postgres. | Production-ready full-stack deployment with reduced bundle footprint | Week 4 (Day 20)